## Ark1
| GANTT CHART | PROJECT NAME | PROJECT DURATION, DAYS | PROJECT START DATE | PROJECT END DATE
|  | Lofthus Frukt og Saft Web site | 25 | 2020-05-11 | 2020-06-05
Task ID | KEY PERSON | Task Description | Task Duration, Days | Start Date | End Date
Menu
1 | Graph. Des. | Create/design menu: positioning/WCAG/colours/fontstyle | 1 | 2020-05-11 | 2020-05-12
2 | Frontend Dev. | Implement html/css; task 1 + add hover and current | 1 | 2020-05-12 | 2020-05-13
| PM | Meet with client - "check up", same page? | 0.5 | 2020-05-14 | 2020-05-14
Delivery
3 | Digital mark. | Create persona(s) | 2 | 2020-05-11 | 2020-05-13
4 | Copywriter | Create text content, use task 3. Explain different opt. | 1 | 2020-05-12 | 2020-05-13
5 | Graph. Des. | Create/design opt. "pick up": button + simple form | 3 | 2020-05-13 | 2020-05-16
6 | Graph. Des. | Create/design opt. "post-delivery": button + simple form | 3 | 2020-05-13 | 2020-05-16
7 | Graph. Des. | Create/design opt. "pick up": button + simple form | 3 | 2020-05-13 | 2020-05-16
8 | Frontend Dev. | Impl. html/css tasks 4 (from CW)+ tasks 5,6,7 (from GD). | 3 | 2020-05-14 | 2020-05-17
| PM | Meet with client - "check up", same page? | 0.5 | 2020-05-18 | 2020-05-18
Order form
9 | Graph. Des. | Create/design button "delete product" | 4 | 2020-05-15 | 2020-05-19
10 | Graph. Des. | Create/design button "adjust quantity" - arrows up/down | 4 | 2020-05-15 | 2020-05-19
11 | Graph. Des. | Create/design button "change delivery option" | 4 | 2020-05-15 | 2020-05-19
12 | Graph. Des. | Create/design checkbox option - "remember me" | 4 | 2020-05-15 | 2020-05-19
13 | Frontend Dev. | Impl. html/css tasks 9,10,11,12 (from GD) | 4 | 2020-05-18 | 2020-05-22
| PM | Meet with client -"check up", same page? | 0.5 | 2020-05-23 | 2020-05-23
Checkout
14 | Copywriter | Write content "terms & conditions" | 3 | 2020-05-13 | 2020-05-16
15 | Graph. Des. | Create/design checkbox opt. - paym. meth. Vipps/CC/Invoice | 4 | 2020-05-22 | 2020-05-26
16 | Graph. Des. | Create/design small form to every paym. meth. | 4 | 2020-05-22 | 2020-05-26
17 | Graph. Des. | Create/design checkbox - "Terms & Conditions" | 4 | 2020-05-22 | 2020-05-26
18 | Graph. Des. | Create/design button "Pay & Checkout" | 4 | 2020-05-22 | 2020-05-26
19 | Frontend Dev. | Impl. html/css tasks 14,15,16,17,18,19 (from CW + GD) | 4 | 2020-05-25 | 2020-05-29
| Total team | Read through/ look through (bugs, text correction, optimize) | 1 | 2020-05-30 | 2020-05-31
| Total team | Corrections/ flicking/ tuning etc. | 2 | 2020-06-01 | 2020-06-03
| PM | Last read through - deliver on deadline | 1 | 2020-06-04 | 2020-06-05
Formulas:
PROJECT END DATE = [PROJECT START DATE]+[PROJECT DURATION, DAYS]